## Rolling Plan
ROLLING PLAN — no-stock SKUs against coil on hand
As on 26 Oct 2026. Demand = "QTY LEFT WITH NO STOCK" (Indent − Dispatch, 1–25 Oct) from QtyLeft_Stock_vs_NoStock_Oct26.xlsx. Coil = unconsumed baby coils (242, 904.52 MT) + unslit mother coils (900.69 MT), live Supabase. Rules: PT Operating System Pack — ADR-0001, campaign-planning-parameters R1–R8.
Sequence: rounds then shapes, diameter ascending (R6); gauge thin→thick inside a family (R5); coil in the yard before coil to be slit (R7.1); ONE window per family (ADR-0001), at most 12 (South) / 5 (West) families per week — the most either region has actually run in one week. Mother coil is on site: slit + buffer = ready 29 Oct, so it can serve W1 — the "Runs from" column dates those lots. The 14-day lead applies only to coil that must be bought.
Thresholds PROPOSED, not signed off: min campaign 20 MT/family, gauge floor 8 MT/cell (×1.5 = 12 MT outside the 3–8% T/D band), coil→tube yield 96%. Verified against the live database on 26 Oct 2026.
Slot | Runs from | Region | Plant (coil sits here) | Section | Size | Gauge mm | Qty left MT | Coil spec needed (th × width) | Coil available: yard MT | Coil available: mother MT | Coil used: yard MT | Coil used: mother MT | PLAN MT | Still short MT | Level 1 test: family vs min campaign | Level 2 test: cell vs gauge floor | T/D band | Status | SKU master | Coil order by | Width basis
W1 27 Oct–1 Nov | 29 Oct | SOUTH | Hyderabad | SHS | 20x20 | 1.6 | 41 | 1.6 × 76 mm | 0 | 18.88 | 0 | 18.88 | 18.12 | 22.88 | 79 / 20 MT ✓ | 41 / 8 MT ✓ | in band | RUN SHORT — coil limits it | ok | 07 Nov 2026 | South has slit this 24 of 47 times
W1 27 Oct–1 Nov | 29 Oct | SOUTH | Hyderabad + Lepakshi | SHS | 20x20 | 2 | 30 | 2 × 76 mm | 4.03 | 27.43 | 4.03 | 27.22 | 30 | 0 | 79 / 20 MT ✓ | 30 / 8 MT ✓ | in band | RUN | ok |  | South has slit this 37 of 57 times
W1 27 Oct–1 Nov | 27 Oct | SOUTH | Lepakshi + Hyderabad | SHS | 25x25 | 2.5 | 12 | 2.5 × 94 mm | 23.77 | 90.47 | 12.5 | 0 | 12 | 0 | 60 / 20 MT ✓ | 12 / 8 MT ✓ | in band | RUN | ok |  | South has slit this 21 of 50 times
W1 27 Oct–1 Nov | 27 Oct | SOUTH | Lepakshi + Hyderabad | SHS | 50x50 | 3 | 8 | 3 × 195 mm | 13.16 | 149.12 | 8.33 | 0 | 8 | 0 | 23 / 20 MT ✓ | 8 / 8 MT ✓ | in band | RUN | ok |  | South has slit this 20 of 20 times
W1 27 Oct–1 Nov | 29 Oct | SOUTH | Hyderabad | SHS | 72x72 | 3 | 14 | 3 × 281 mm | 0 | 149.12 | 0 | 14.58 | 14 | 0 | 39 / 20 MT ✓ | 14 / 8 MT ✓ | in band | RUN | ok |  | South has slit this 6 of 6 times
W1 27 Oct–1 Nov | 27 Oct | SOUTH | Hyderabad | SHS | 100x100 | 1.6 | 20 | 1.6 × 398 mm | 14.6 | 0 | 14.6 | 0 | 14.02 | 5.98 | 150 / 20 MT ✓ | 20 / 12 MT ✓ | BAND EDGE | RUN SHORT — coil limits it | ok | 07 Nov 2026 | South width from its own 2mm run (1.6mm never run here)
W1 27 Oct–1 Nov | 29 Oct | SOUTH | Lepakshi + Hyderabad | SHS | 100x100 | 2.5 | 41 | 2.5 × 397 mm | 27.72 | 90.47 | 27.72 | 14.99 | 41 | 0 | 150 / 20 MT ✓ | 41 / 12 MT ✓ | BAND EDGE | RUN | ok |  | South has slit this 4 of 4 times
W1 27 Oct–1 Nov | 29 Oct | SOUTH | Hyderabad | SHS | 100x100 | 2.8 | 12 | 2.8 × 395 mm | 0 | 166.94 | 0 | 12.5 | 12 | 0 | 150 / 20 MT ✓ | 12 / 12 MT ✓ | BAND EDGE | RUN | ok |  | South width from its own 3mm run (2.8mm never run here)
W1 27 Oct–1 Nov | 27 Oct | SOUTH | Lepakshi + Hyderabad | SHS | 100x100 | 4 | 22 | 4 × 391 mm | 35.63 | 0 | 22.92 | 0 | 22 | 0 | 150 / 20 MT ✓ | 22 / 8 MT ✓ | in band | RUN | ok |  | South has slit this 5 of 5 times
W1 27 Oct–1 Nov | 29 Oct | SOUTH | Hyderabad | RHS | 80x40 | 3 | 8 | 3 × 235 mm | 4.12 | 125.61 | 4.12 | 4.21 | 8 | 0 | 97 / 20 MT ✓ | 8 / 8 MT ✓ | in band | RUN | ok |  | South width from its own 2.8mm run (3mm never run here)
W1 27 Oct–1 Nov | 29 Oct | WEST | NPMD | SHS | 20x20 | 1.6 | 15 | 1.6 × 76 mm | 0 | 406.75 | 0 | 15.62 | 15 | 0 | 27 / 20 MT ✓ | 15 / 8 MT ✓ | in band | RUN | ok |  | company-wide width — West has never run this size
W1 27 Oct–1 Nov | 29 Oct | WEST | NPMD | SHS | 25x25 | 1.6 | 11 | 1.6 × 97 mm | 1.73 | 391.12 | 1.73 | 9.73 | 11 | 0 | 71 / 20 MT ✓ | 11 / 8 MT ✓ | in band | RUN | ok |  | company-wide width — West has never run this size
W1 27 Oct–1 Nov | 29 Oct | WEST | NPMD | SHS | 25x25 | 2.5 | 14 | 2.5 × 94 mm | 0 | 49 | 0 | 14.58 | 14 | 0 | 71 / 20 MT ✓ | 14 / 8 MT ✓ | in band | RUN | ok |  | company-wide width — West has never run this size
W1 27 Oct–1 Nov | 29 Oct | WEST | Tapi + NPMD | SHS | 25x25 | 3 | 12 | 3 × 95 mm | 1.98 | 75.97 | 1.98 | 10.52 | 12 | 0 | 71 / 20 MT ✓ | 12 / 12 MT ✓ | BAND EDGE | RUN | ok |  | company-wide width from 2.8mm — West has never run this size
W1 27 Oct–1 Nov | 29 Oct | WEST | NPMD | SHS | 40x40 | 1.6 | 38 | 1.6 × 159 mm | 0 | 381.39 | 0 | 39.58 | 38 | 0 | 245 / 20 MT ✓ | 38 / 8 MT ✓ | in band | RUN | ok |  | West width from its own 2mm run (1.6mm never run here)
W1 27 Oct–1 Nov | 29 Oct | WEST | NPMD | SHS | 40x40 | 2.5 | 22 | 2.5 × 159 mm | 0 | 34.42 | 0 | 22.92 | 22 | 0 | 245 / 20 MT ✓ | 22 / 8 MT ✓ | in band | RUN | ok |  | West width from its own 2mm run (2.5mm never run here)
W1 27 Oct–1 Nov | 29 Oct | WEST | NPMD | SHS | 40x40 | 3 | 53 | 3 × 156 mm | 26.73 | 65.46 | 26.73 | 28.48 | 53 | 0 | 245 / 20 MT ✓ | 53 / 8 MT ✓ | in band | RUN | ok |  | West has slit this 1 of 1 times
W1 27 Oct–1 Nov | 29 Oct | WEST | NPMD | SHS | 60x60 | 3 | 18 | 3 × 235 mm | 0 | 36.98 | 0 | 18.75 | 18 | 0 | 56 / 20 MT ✓ | 18 / 8 MT ✓ | in band | RUN | ok |  | company-wide width from 2.8mm — West has never run this size
W1 27 Oct–1 Nov | 27 Oct | WEST | Tapi | SHS | 60x60 | 4 | 14 | 4 × 230 mm | 27.6 | 0 | 14.58 | 0 | 14 | 0 | 56 / 20 MT ✓ | 14 / 8 MT ✓ | in band | RUN | ok |  | company-wide width — West has never run this size
W1 27 Oct–1 Nov | 27 Oct | WEST | Tapi | SHS | 60x60 | 5 | 13 | 5 × 230 mm | 23.08 | 0 | 13.54 | 0 | 13 | 0 | 56 / 20 MT ✓ | 13 / 8 MT ✓ | in band | RUN | ok |  | company-wide width from 4mm — West has never run this size
W1 27 Oct–1 Nov | 29 Oct | WEST | NPMD | SHS | 72x72 | 1.6 | 21 | 1.6 × 288 mm | 4.68 | 341.8 | 4.68 | 17.19 | 21 | 0 | 40 / 20 MT ✓ | 21 / 12 MT ✓ | BAND EDGE | RUN | ok |  | West width from its own 2mm run (1.6mm never run here)
W1 27 Oct–1 Nov | 27 Oct | WEST | Tapi | SHS | 72x72 | 4 | 16 | 4 × 286 mm | 24.44 | 0 | 16.67 | 0 | 16 | 0 | 40 / 20 MT ✓ | 16 / 8 MT ✓ | in band | RUN | ok |  | West has slit this 5 of 7 times
W2 3–8 Nov | 03 Nov | WEST | Tapi | SHS | 80x80 | 4 | 15 | 4 × 316 mm | 11.42 | 0 | 11.42 | 0 | 10.96 | 4.04 | 49 / 20 MT ✓ | 15 / 8 MT ✓ | in band | RUN SHORT — coil limits it | ok | 07 Nov 2026 | West has slit this 4 of 8 times
W2 3–8 Nov | 03 Nov | WEST | NPMD | SHS | 100x100 | 1.6 | 33 | 1.6 × 398 mm | 0 | 324.61 | 0 | 34.38 | 33 | 0 | 115 / 20 MT ✓ | 33 / 12 MT ✓ | BAND EDGE | RUN | ok |  | West width from its own 2mm run (1.6mm never run here)
W2 3–8 Nov | 03 Nov | WEST | NPMD | RHS | 40x20 | 1.6 | 10 | 1.6 × 116 mm | 0 | 290.24 | 0 | 10.42 | 10 | 0 | 37 / 20 MT ✓ | 10 / 8 MT ✓ | in band | RUN | ok |  | company-wide width — West has never run this size
W2 3–8 Nov | 03 Nov | WEST | NPMD | RHS | 50x25 | 2.5 | 11 | 2.5 × 147 mm | 0 | 11.5 | 0 | 11.46 | 11 | 0 | 67 / 20 MT ✓ | 11 / 8 MT ✓ | in band | RUN | ok |  | West has slit this 5 of 5 times
W2 3–8 Nov | 03 Nov | WEST | Tapi | RHS | 122x61 | 4 | 28 | 4 × 360 mm | 18.86 | 0 | 18.86 | 0 | 18.11 | 9.89 | 47 / 20 MT ✓ | 28 / 8 MT ✓ | in band | RUN SHORT — coil limits it | ok | 07 Nov 2026 | West has slit this 4 of 8 times
Order coil |  | SOUTH | — | SHS | 50x50 | 1.2 | 15 | 1.2 × 198 mm | 0 | 0 | 0 | 0 | 0 | 15 | 23 / 20 MT ✓ | 15 / 12 MT ✓ | BAND EDGE | NO COIL — order 1.2 mm × 198 mm | ok | 07 Nov 2026 | South has slit this 10 of 17 times
Order coil |  | SOUTH | — | SHS | 72x72 | 1.6 | 20 | 1.6 × 286 mm | 0 | 0 | 0 | 0 | 0 | 20 | 39 / 20 MT ✓ | 20 / 12 MT ✓ | BAND EDGE | NO COIL — order 1.6 mm × 286 mm | ok | 07 Nov 2026 | South width from its own 2mm run (1.6mm never run here)
Order coil |  | SOUTH | — | RHS | 50x25 | 1.2 | 23 | 1.2 × 148 mm | 0 | 0 | 0 | 0 | 0 | 23 | 37 / 20 MT ✓ | 23 / 12 MT ✓ | BAND EDGE | NO COIL — order 1.2 mm × 148 mm | ok | 07 Nov 2026 | South width from its own 1.6mm run (1.2mm never run here)
Order coil |  | SOUTH | — | RHS | 50x25 | 1.6 | 14 | 1.6 × 148 mm | 0 | 0 | 0 | 0 | 0 | 14 | 37 / 20 MT ✓ | 14 / 8 MT ✓ | in band | NO COIL — order 1.6 mm × 148 mm | ok | 07 Nov 2026 | South has slit this 27 of 38 times
Order coil |  | SOUTH | — | RHS | 60x40 | 1.2 | 32 | 1.2 × 197 mm | 0 | 0 | 0 | 0 | 0 | 32 | 68 / 20 MT ✓ | 32 / 12 MT ✓ | BAND EDGE | NO COIL — order 1.2 mm × 197 mm | ok | 07 Nov 2026 | South width from its own 1.6mm run (1.2mm never run here)
Order coil |  | SOUTH | — | RHS | 75x25 | 1.2 | 20 | 1.2 × 197 mm | 0 | 0 | 0 | 0 | 0 | 20 | 34 / 20 MT ✓ | 20 / 12 MT ✓ | BAND EDGE | NO COIL — order 1.2 mm × 197 mm | ok | 07 Nov 2026 | South width from its own 1.6mm run (1.2mm never run here)
Order coil |  | SOUTH | — | RHS | 60x40 | 1.6 | 28 | 1.6 × 197 mm | 0 | 0 | 0 | 0 | 0 | 28 | 68 / 20 MT ✓ | 28 / 12 MT ✓ | BAND EDGE | NO COIL — order 1.6 mm × 197 mm | ok | 07 Nov 2026 | South has slit this 64 of 64 times
Order coil |  | SOUTH | — | RHS | 75x25 | 1.6 | 14 | 1.6 × 197 mm | 0 | 0 | 0 | 0 | 0 | 14 | 34 / 20 MT ✓ | 14 / 12 MT ✓ | BAND EDGE | NO COIL — order 1.6 mm × 197 mm | ok | 07 Nov 2026 | South has slit this 22 of 22 times
Order coil |  | SOUTH | — | RHS | 80x40 | 1.2 | 19 | 1.2 × 237 mm | 0 | 0 | 0 | 0 | 0 | 19 | 97 / 20 MT ✓ | 19 / 12 MT ✓ | BAND EDGE | NO COIL — order 1.2 mm × 237 mm | ok | 07 Nov 2026 | South width from its own 1.6mm run (1.2mm never run here)
Order coil |  | SOUTH | — | RHS | 96x48 | 1.6 | 37 | 1.6 × 286 mm | 0 | 0 | 0 | 0 | 0 | 37 | 43 / 20 MT ✓ | 37 / 12 MT ✓ | BAND EDGE | NO COIL — order 1.6 mm × 286 mm | ok | 07 Nov 2026 | South width from its own 2mm run (1.6mm never run here)
Order coil |  | SOUTH | — | RHS | 100x50 | 1.6 | 46 | 1.6 × 296 mm | 0 | 0 | 0 | 0 | 0 | 46 | 51 / 20 MT ✓ | 46 / 12 MT ✓ | BAND EDGE | NO COIL — order 1.6 mm × 296 mm | ok | 07 Nov 2026 | South has slit this 9 of 18 times
Order coil |  | WEST | — | SHS | 20x20 | 2 | 9 | 2 × 76 mm | 0 | 0 | 0 | 0 | 0 | 9 | 27 / 20 MT ✓ | 9 / 8 MT ✓ | in band | NO COIL — order 2 mm × 76 mm | ok | 07 Nov 2026 | company-wide width — West has never run this size
Order coil |  | WEST | — | SHS | 25x25 | 2 | 14 | 2 × 97 mm | 0 | 0 | 0 | 0 | 0 | 14 | 71 / 20 MT ✓ | 14 / 8 MT ✓ | in band | NO COIL — order 2 mm × 97 mm | ok | 07 Nov 2026 | company-wide width — West has never run this size
Order coil |  | WEST | — | SHS | 40x40 | 1.2 | 33 | 1.2 × 159 mm | 0 | 0 | 0 | 0 | 0 | 33 | 245 / 20 MT ✓ | 33 / 12 MT ✓ | BAND EDGE | NO COIL — order 1.2 mm × 159 mm | ok | 07 Nov 2026 | West width from its own 2mm run (1.2mm never run here)
Order coil |  | WEST | — | SHS | 40x40 | 2 | 50 | 2 × 159 mm | 0 | 0 | 0 | 0 | 0 | 50 | 245 / 20 MT ✓ | 50 / 8 MT ✓ | in band | NO COIL — order 2 mm × 159 mm | ok | 07 Nov 2026 | West has slit this 1 of 1 times
Order coil |  | WEST | — | SHS | 40x40 | 4 | 42 | 4 × 156 mm | 0 | 0 | 0 | 0 | 0 | 42 | 245 / 20 MT ✓ | 42 / 8 MT ✓ | in band | NO COIL — order 4 mm × 156 mm | ok | 07 Nov 2026 | West width from its own 3mm run (4mm never run here)
Order coil |  | WEST | — | SHS | 80x80 | 5 | 19 | 5 × 314 mm | 0 | 0 | 0 | 0 | 0 | 19 | 49 / 20 MT ✓ | 19 / 8 MT ✓ | in band | NO COIL — order 5 mm × 314 mm | ok | 07 Nov 2026 | West has slit this 2 of 2 times
Order coil |  | WEST | — | SHS | 100x100 | 4 | 46 | 4 × 395 mm | 0 | 0 | 0 | 0 | 0 | 46 | 115 / 20 MT ✓ | 46 / 8 MT ✓ | in band | NO COIL — order 4 mm × 395 mm | ok | 07 Nov 2026 | West has slit this 6 of 9 times
Order coil |  | WEST | — | SHS | 100x100 | 5 | 36 | 5 × 395 mm | 0 | 0 | 0 | 0 | 0 | 36 | 115 / 20 MT ✓ | 36 / 8 MT ✓ | in band | NO COIL — order 5 mm × 395 mm | ok | 07 Nov 2026 | West has slit this 7 of 7 times
Order coil |  | WEST | — | SHS | 150x150 | 6 | 33 | 6 × 596 mm | 0 | 0 | 0 | 0 | 0 | 33 | 38 / 20 MT ✓ | 33 / 8 MT ✓ | in band | NO COIL — order 6 mm × 596 mm | ok | 07 Nov 2026 | West width from its own 5mm run (6mm never run here)
Order coil |  | WEST | — | RHS | 40x20 | 2 | 16 | 2 × 116 mm | 0 | 0 | 0 | 0 | 0 | 16 | 37 / 20 MT ✓ | 16 / 8 MT ✓ | in band | NO COIL — order 2 mm × 116 mm | ok | 07 Nov 2026 | company-wide width — West has never run this size
Order coil |  | WEST | — | RHS | 50x25 | 1.2 | 25 | 1.2 × 149 mm | 0 | 0 | 0 | 0 | 0 | 25 | 67 / 20 MT ✓ | 25 / 12 MT ✓ | BAND EDGE | NO COIL — order 1.2 mm × 149 mm | ok | 07 Nov 2026 | West width from its own 1.6mm run (1.2mm never run here)
Order coil |  | WEST | — | RHS | 60x40 | 1.2 | 20 | 1.2 × 200 mm | 0 | 0 | 0 | 0 | 0 | 20 | 22 / 20 MT ✓ | 20 / 12 MT ✓ | BAND EDGE | NO COIL — order 1.2 mm × 200 mm | ok | 07 Nov 2026 | West width from its own 1.6mm run (1.2mm never run here)
Order coil |  | WEST | — | RHS | 122x61 | 5 | 19 | 5 × 358 mm | 0 | 0 | 0 | 0 | 0 | 19 | 47 / 20 MT ✓ | 19 / 8 MT ✓ | in band | NO COIL — order 5 mm × 358 mm | ok | 07 Nov 2026 | West has slit this 3 of 3 times
Order coil |  | WEST | — | RHS | 145x82 | 5 | 21 | 5 × 448 mm | 0 | 0 | 0 | 0 | 0 | 21 | 29 / 20 MT ✓ | 21 / 8 MT ✓ | in band | NO COIL — order 5 mm × 448 mm | ok | 07 Nov 2026 | West width from its own 4mm run (5mm never run here)
Order coil |  | WEST | — | RHS | 200x100 | 4 | 32 | 4 × 596 mm | 0 | 0 | 0 | 0 | 0 | 32 | 62 / 20 MT ✓ | 32 / 12 MT ✓ | BAND EDGE | NO COIL — order 4 mm × 596 mm | ok | 07 Nov 2026 | West has slit this 3 of 3 times
Order coil |  | WEST | — | RHS | 200x100 | 6 | 30 | 6 × 596 mm | 0 | 0 | 0 | 0 | 0 | 30 | 62 / 20 MT ✓ | 30 / 8 MT ✓ | in band | NO COIL — order 6 mm × 596 mm | ok | 07 Nov 2026 | West width from its own 5mm run (6mm never run here)
Fix master |  | SOUTH | — | CHS | 25 NB | 3 | 4 | 3 × 96 mm | 13.63 | 149.12 | 0 | 0 | 0 | 4 | 12 / 20 MT ✗ | 4 / 12 MT ✗ | BAND EDGE | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | South width from its own 2.8mm run (3mm never run here)
Fix master |  | SOUTH | — | CHS | 32 NB | 3 | 4 | 3 × 128 mm | 0 | 149.12 | 0 | 0 | 0 | 4 | 4 / 20 MT ✗ | 4 / 8 MT ✗ | in band | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | South width from its own 2.8mm run (3mm never run here)
Fix master |  | SOUTH | — | CHS | 40 NB | 3 | 6 | 3 × 148 mm | 7.76 | 149.12 | 0 | 0 | 0 | 6 | 22 / 20 MT ✓ | 6 / 8 MT ✗ | in band | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | South width from its own 2.9mm run (3mm never run here)
Fix master |  | SOUTH | — | CHS | 65 NB | 3 | 4 | 3 × 234 mm | 4.12 | 149.12 | 0 | 0 | 0 | 4 | 4 / 20 MT ✗ | 4 / 8 MT ✗ | in band | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | South width from its own 2.8mm run (3mm never run here)
Fix master |  | SOUTH | — | CHS | 80 NB | 3.5 | 4 | 3.5 × 272 mm | 8.43 | 43.08 | 0 | 0 | 0 | 4 | 4 / 20 MT ✗ | 4 / 8 MT ✗ | in band | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | South width from its own 3.2mm run (3.5mm never run here)
Fix master |  | SOUTH | — | CHS | 100 NB | 2 | 4 | 2 × ? mm | 0 | 27.43 | 0 | 0 | 0 | 4 | 21 / 20 MT ✓ | 4 / 12 MT ✗ | BAND EDGE | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | never run anywhere — slitting spec needed
Fix master |  | SOUTH | — | CHS | 100 NB | 2.5 | 4 | 2.5 × ? mm | 0 | 90.47 | 0 | 0 | 0 | 4 | 21 / 20 MT ✓ | 4 / 12 MT ✗ | BAND EDGE | BLOCKED — no slitting spec: width never established | ok |  | never run anywhere — slitting spec needed
Fix master |  | SOUTH | — | CHS | 100 NB | 3 | 4 | 3 × ? mm | 0 | 149.12 | 0 | 0 | 0 | 4 | 21 / 20 MT ✓ | 4 / 12 MT ✗ | BAND EDGE | BLOCKED — no slitting spec: width never established | ok |  | never run anywhere — slitting spec needed
Fix master |  | SOUTH | — | CHS | 100 NB | 4 | 4 | 4 × ? mm | 0 | 0 | 0 | 0 | 0 | 4 | 21 / 20 MT ✓ | 4 / 8 MT ✗ | in band | BLOCKED — no slitting spec: width never established | ok |  | never run anywhere — slitting spec needed
Fix master |  | SOUTH | — | CHS | 100 NB | 5 | 5 | 5 × ? mm | 0 | 83.06 | 0 | 0 | 0 | 5 | 21 / 20 MT ✓ | 5 / 8 MT ✗ | in band | BLOCKED — no slitting spec: width never established | ok |  | never run anywhere — slitting spec needed
Fix master |  | SOUTH | — | CHS | 125 NB | 3 | 4 | 3 × ? mm | 0 | 149.12 | 0 | 0 | 0 | 4 | 8 / 20 MT ✗ | 4 / 12 MT ✗ | BAND EDGE | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | never run anywhere — slitting spec needed
Fix master |  | SOUTH | — | CHS | 125 NB | 4 | 4 | 4 × ? mm | 0 | 0 | 0 | 0 | 0 | 4 | 8 / 20 MT ✗ | 4 / 12 MT ✗ | BAND EDGE | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | never run anywhere — slitting spec needed
Fix master |  | SOUTH | — | CHS | 150 NB | 3 | 4 | 3 × ? mm | 0 | 149.12 | 0 | 0 | 0 | 4 | 13 / 20 MT ✗ | 4 / 12 MT ✗ | BAND EDGE | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | never run anywhere — slitting spec needed
Fix master |  | SOUTH | — | CHS | 150 NB | 4 | 4 | 4 × ? mm | 0 | 0 | 0 | 0 | 0 | 4 | 13 / 20 MT ✗ | 4 / 12 MT ✗ | BAND EDGE | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | never run anywhere — slitting spec needed
Fix master |  | SOUTH | — | CHS | 150 NB | 5 | 5 | 5 × ? mm | 0 | 83.06 | 0 | 0 | 0 | 5 | 13 / 20 MT ✗ | 5 / 8 MT ✗ | in band | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | never run anywhere — slitting spec needed
Fix master |  | SOUTH | — | SHS | 80x80 | 2 | 6 | 2 × 315 mm | 0 | 0.21 | 0 | 0 | 0 | 6 | 21 / 20 MT ✓ | 6 / 12 MT ✗ | BAND EDGE | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | company-wide width from 2.5mm — South has never run this size
Fix master |  | SOUTH | — | SHS | 80x80 | 2.8 | 6 | 2.8 × 315 mm | 0 | 181.93 | 0 | 0 | 0 | 6 | 21 / 20 MT ✓ | 6 / 12 MT ✗ | BAND EDGE | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | company-wide width from 3mm — South has never run this size
Fix master |  | SOUTH | — | RHS | 95x25 | 2 | 6 | 2 × ? mm | 0 | 0.21 | 0 | 0 | 0 | 6 | 6 / 20 MT ✗ | 6 / 12 MT ✗ | BAND EDGE | BLOCKED — no slitting spec: width never established | ok |  | never run anywhere — slitting spec needed
Fix master |  | WEST | — | CHS | 20 NB | 1.2 | 5 | 1.2 × 76 mm | 0 | 0 | 0 | 0 | 0 | 5 | 12 / 20 MT ✗ | 5 / 8 MT ✗ | in band | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | company-wide width from 1.6mm — West has never run this size
Fix master |  | WEST | — | CHS | 32 NB | 5 | 4 | 5 × 128 mm | 0 | 0 | 0 | 0 | 0 | 4 | 11 / 20 MT ✗ | 4 / 12 MT ✗ | BAND EDGE | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | company-wide width from 4mm — West has never run this size
Fix master |  | WEST | — | CHS | 40 NB | 3 | 9 | 3 × 148 mm | 12.34 | 75.97 | 0 | 0 | 0 | 9 | 14 / 20 MT ✗ | 9 / 8 MT ✓ | in band | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | company-wide width from 2.9mm — West has never run this size
Fix master |  | WEST | — | CHS | 50 NB | 3 | 5 | 3 × 186 mm | 0 | 75.97 | 0 | 0 | 0 | 5 | 9 / 20 MT ✗ | 5 / 8 MT ✗ | in band | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | company-wide width from 2.8mm — West has never run this size
Fix master |  | WEST | — | SHS | 20x20 | 2.5 | 3 | 2.5 × 76 mm | 0 | 49 | 0 | 0 | 0 | 3 | 27 / 20 MT ✓ | 3 / 12 MT ✗ | BAND EDGE | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | company-wide width from 2mm — West has never run this size
Fix master |  | WEST | — | SHS | 32x32 | 1.6 | 10 | 1.6 × ? mm | 0 | 381.39 | 0 | 0 | 0 | 10 | 36 / 20 MT ✓ | 10 / 8 MT ✓ | in band | BLOCKED — no slitting spec: width never established | ok |  | never run anywhere — slitting spec needed
Fix master |  | WEST | — | SHS | 32x32 | 2 | 10 | 2 × ? mm | 0 | 0 | 0 | 0 | 0 | 10 | 36 / 20 MT ✓ | 10 / 8 MT ✓ | in band | BLOCKED — no slitting spec: width never established | ok |  | never run anywhere — slitting spec needed
Fix master |  | WEST | — | SHS | 32x32 | 2.5 | 5 | 2.5 × ? mm | 0 | 34.42 | 0 | 0 | 0 | 5 | 36 / 20 MT ✓ | 5 / 8 MT ✗ | in band | BLOCKED — no slitting spec: width never established | ok |  | never run anywhere — slitting spec needed
Fix master |  | WEST | — | SHS | 32x32 | 3 | 11 | 3 × ? mm | 0 | 65.46 | 0 | 0 | 0 | 11 | 36 / 20 MT ✓ | 11 / 8 MT ✓ | in band | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | never run anywhere — slitting spec needed
Fix master |  | WEST | — | SHS | 40x40 | 5 | 7 | 5 × 156 mm | 0 | 0 | 0 | 0 | 0 | 7 | 245 / 20 MT ✓ | 7 / 12 MT ✗ | BAND EDGE | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | West width from its own 3mm run (5mm never run here)
Fix master |  | WEST | — | SHS | 72x72 | 6 | 3 | 6 × 284 mm | 0 | 0 | 0 | 0 | 0 | 3 | 40 / 20 MT ✓ | 3 / 8 MT ✗ | in band | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | West width from its own 5mm run (6mm never run here)
Fix master |  | WEST | — | SHS | 80x80 | 2 | 5 | 2 × 315 mm | 0 | 0 | 0 | 0 | 0 | 5 | 49 / 20 MT ✓ | 5 / 12 MT ✗ | BAND EDGE | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | West width from its own 2.5mm run (2mm never run here)
Fix master |  | WEST | — | SHS | 91x91 | 3 | 2 | 3 × ? mm | 0 | 18.23 | 0 | 0 | 0 | 2 | 10 / 20 MT ✗ | 2 / 12 MT ✗ | BAND EDGE | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | never run anywhere — slitting spec needed
Fix master |  | WEST | — | SHS | 91x91 | 4 | 3 | 4 × ? mm | 0 | 0 | 0 | 0 | 0 | 3 | 10 / 20 MT ✗ | 3 / 8 MT ✗ | in band | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | never run anywhere — slitting spec needed
Fix master |  | WEST | — | SHS | 91x91 | 5 | 5 | 5 × ? mm | 0 | 0 | 0 | 0 | 0 | 5 | 10 / 20 MT ✗ | 5 / 8 MT ✗ | in band | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | never run anywhere — slitting spec needed
Fix master |  | WEST | — | SHS | 113x113 | 5 | 12 | 5 × ? mm | 0 | 0 | 0 | 0 | 0 | 12 | 12 / 20 MT ✗ | 12 / 8 MT ✓ | in band | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | never run anywhere — slitting spec needed
Fix master |  | WEST | — | SHS | 150x150 | 8 | 5 | 8 × 596 mm | 0 | 0 | 0 | 0 | 0 | 5 | 38 / 20 MT ✓ | 5 / 8 MT ✗ | in band | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | West width from its own 5mm run (8mm never run here)
Fix master |  | WEST | — | SHS | 180x180 | 4 | 3 | 4 × ? mm | 0 | 0 | 0 | 0 | 0 | 3 | 8 / 20 MT ✗ | 3 / 12 MT ✗ | BAND EDGE | BLOCKED — no slitting spec: width never established | ok |  | never run anywhere — slitting spec needed
Fix master |  | WEST | — | SHS | 180x180 | 5 | 5 | 5 × ? mm | 0 | 0 | 0 | 0 | 0 | 5 | 8 / 20 MT ✗ | 5 / 12 MT ✗ | BAND EDGE | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | never run anywhere — slitting spec needed
Fix master |  | WEST | — | SHS | 200x200 | 5 | 4 | 5 × ? mm | 0 | 0 | 0 | 0 | 0 | 4 | 13 / 20 MT ✗ | 4 / 12 MT ✗ | BAND EDGE | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | never run anywhere — slitting spec needed
Fix master |  | WEST | — | SHS | 200x200 | 6 | 5 | 6 × ? mm | 0 | 0 | 0 | 0 | 0 | 5 | 13 / 20 MT ✗ | 5 / 12 MT ✗ | BAND EDGE | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | never run anywhere — slitting spec needed
Fix master |  | WEST | — | SHS | 200x200 | 8 | 4 | 8 × ? mm | 0 | 0 | 0 | 0 | 0 | 4 | 13 / 20 MT ✗ | 4 / 8 MT ✗ | in band | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | never run anywhere — slitting spec needed
Fix master |  | WEST | — | RHS | 60x40 | 5 | 2 | 5 × 194 mm | 7.79 | 0 | 0 | 0 | 0 | 2 | 22 / 20 MT ✓ | 2 / 8 MT ✗ | in band | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | West width from its own 4mm run (5mm never run here)
Fix master |  | WEST | — | RHS | 18x180 | 4 | 3 | 4 × ? mm | 0 | 0 | 0 | 0 | 0 | 3 | 3 / 20 MT ✗ | 3 / 8 MT ✗ | in band | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | never run anywhere — slitting spec needed
Fix master |  | WEST | — | RHS | 145x82 | 2 | 3 | 2 × 448 mm | 0 | 0 | 0 | 0 | 0 | 3 | 29 / 20 MT ✓ | 3 / 12 MT ✗ | BAND EDGE | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | West width from its own 3mm run (2mm never run here)
Fix master |  | WEST | — | RHS | 145x82 | 6 | 5 | 6 × 448 mm | 0 | 0 | 0 | 0 | 0 | 5 | 29 / 20 MT ✓ | 5 / 8 MT ✗ | in band | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | West width from its own 4mm run (6mm never run here)
Fix master |  | WEST | — | RHS | 172x92 | 3 | 5 | 3 × ? mm | 0 | 18.23 | 0 | 0 | 0 | 5 | 26 / 20 MT ✓ | 5 / 12 MT ✗ | BAND EDGE | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | never run anywhere — slitting spec needed
Fix master |  | WEST | — | RHS | 172x92 | 4 | 8 | 4 × ? mm | 0 | 0 | 0 | 0 | 0 | 8 | 26 / 20 MT ✓ | 8 / 12 MT ✗ | BAND EDGE | BLOCKED — no slitting spec: width never established | ok |  | never run anywhere — slitting spec needed
Fix master |  | WEST | — | RHS | 172x92 | 5 | 10 | 5 × ? mm | 0 | 0 | 0 | 0 | 0 | 10 | 26 / 20 MT ✓ | 10 / 12 MT ✗ | BAND EDGE | BLOCKED — no slitting spec: width never established | ok |  | never run anywhere — slitting spec needed
Fix master |  | WEST | — | RHS | 172x92 | 6 | 3 | 6 × ? mm | 0 | 0 | 0 | 0 | 0 | 3 | 26 / 20 MT ✓ | 3 / 8 MT ✗ | in band | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | never run anywhere — slitting spec needed
Fix master |  | WEST | — | RHS | 240x120 | 4 | 3 | 4 × ? mm | 0 | 0 | 0 | 0 | 0 | 3 | 17 / 20 MT ✗ | 3 / 12 MT ✗ | BAND EDGE | BLOCKED — no slitting spec: width never established | ok |  | never run anywhere — slitting spec needed
Fix master |  | WEST | — | RHS | 240x120 | 5 | 9 | 5 × ? mm | 0 | 0 | 0 | 0 | 0 | 9 | 17 / 20 MT ✗ | 9 / 12 MT ✗ | BAND EDGE | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | never run anywhere — slitting spec needed
Fix master |  | WEST | — | RHS | 240x120 | 6 | 5 | 6 × ? mm | 0 | 0 | 0 | 0 | 0 | 5 | 17 / 20 MT ✗ | 5 / 12 MT ✗ | BAND EDGE | BLOCKED — no SKU master row for this size × gauge | NO SKU ROW |  | never run anywhere — slitting spec needed
Next cycle |  | SOUTH | — | CHS | 25 NB | 4 | 8 | 3.7 × 95 mm | 0 | 0 | 0 | 0 | 0 | 8 | 12 / 20 MT ✗ | 8 / 12 MT ✗ | BAND EDGE | DEFER — family short of min campaign | ok |  | South has slit this 3 of 3 times
Next cycle |  | SOUTH | — | CHS | 40 NB | 1.2 | 10 | 1.2 × 150 mm | 0 | 0 | 0 | 0 | 0 | 10 | 22 / 20 MT ✓ | 10 / 12 MT ✗ | BAND EDGE | DEFER — under gauge floor | ok |  | South width from its own 1.6mm run (1.2mm never run here)
Next cycle |  | SOUTH | — | CHS | 40 NB | 1.6 | 6 | 1.6 × 150 mm | 0 | 18.88 | 0 | 0 | 0 | 6 | 22 / 20 MT ✓ | 6 / 8 MT ✗ | in band | DEFER — under gauge floor | ok |  | South has slit this 14 of 14 times
Next cycle |  | SOUTH | — | CHS | 50 NB | 1.2 | 10 | 1.2 × 185 mm | 0 | 0 | 0 | 0 | 0 | 10 | 16 / 20 MT ✗ | 10 / 12 MT ✗ | BAND EDGE | DEFER — family short of min campaign | ok |  | South width from its own 1.6mm run (1.2mm never run here)
Next cycle |  | SOUTH | — | CHS | 50 NB | 4 | 6 | 4 × 182 mm | 6.16 | 0 | 0 | 0 | 0 | 6 | 16 / 20 MT ✗ | 6 / 8 MT ✗ | in band | DEFER — family short of min campaign | ok |  | South has slit this 3 of 3 times
Next cycle |  | SOUTH | — | SHS | 15x15 | 1.6 | 5 | 1.6 × 64 mm | 5.85 | 18.88 | 0 | 0 | 0 | 5 | 5 / 20 MT ✗ | 5 / 8 MT ✗ | in band | DEFER — family short of min campaign | ok |  | South has slit this 2 of 2 times
Next cycle |  | SOUTH | — | SHS | 20x20 | 1.2 | 8 | 1.2 × 77 mm | 1.12 | 0 | 0 | 0 | 0 | 8 | 79 / 20 MT ✓ | 8 / 8 MT ✓ | in band | DEFER — only 1.1 MT of coil, under the 8 MT gauge floor | ok | 07 Nov 2026 | South has slit this 24 of 28 times
Next cycle |  | SOUTH | — | SHS | 25x25 | 1.2 | 26 | 1.2 × 97 mm | 1.59 | 0 | 0 | 0 | 0 | 26 | 60 / 20 MT ✓ | 26 / 8 MT ✓ | in band | DEFER — only 1.5 MT of coil, under the 8 MT gauge floor | ok | 07 Nov 2026 | South has slit this 12 of 20 times
Next cycle |  | SOUTH | — | SHS | 25x25 | 1.6 | 22 | 1.6 × 97 mm | 1.57 | 0 | 0 | 0 | 0 | 22 | 60 / 20 MT ✓ | 22 / 8 MT ✓ | in band | DEFER — only 1.5 MT of coil, under the 8 MT gauge floor | ok | 07 Nov 2026 | South has slit this 74 of 92 times
Next cycle |  | SOUTH | — | SHS | 30x30 | 1.2 | 5 | 1.2 × 116 mm | 0 | 0 | 0 | 0 | 0 | 5 | 41 / 20 MT ✓ | 5 / 12 MT ✗ | BAND EDGE | DEFER — under gauge floor | ok |  | South width from its own 1.6mm run (1.2mm never run here)
Next cycle |  | SOUTH | — | SHS | 30x30 | 1.6 | 16 | 1.6 × 116 mm | 4.22 | 0 | 0 | 0 | 0 | 16 | 41 / 20 MT ✓ | 16 / 8 MT ✓ | in band | DEFER — only 4.1 MT of coil, under the 8 MT gauge floor | ok | 07 Nov 2026 | South has slit this 21 of 24 times
Next cycle |  | SOUTH | — | SHS | 30x30 | 2 | 20 | 2 × 116 mm | 3.89 | 0.21 | 0 | 0 | 0 | 20 | 41 / 20 MT ✓ | 20 / 8 MT ✓ | in band | DEFER — only 3.9 MT of coil, under the 8 MT gauge floor | ok | 07 Nov 2026 | South has slit this 16 of 17 times
Next cycle |  | SOUTH | — | SHS | 38x38 | 1.2 | 10 | 1.2 × 148 mm | 0 | 0 | 0 | 0 | 0 | 10 | 14 / 20 MT ✗ | 10 / 12 MT ✗ | BAND EDGE | DEFER — family short of min campaign | ok |  | South width from its own 1.6mm run (1.2mm never run here)
Next cycle |  | SOUTH | — | SHS | 38x38 | 4 | 4 | 3.7 × 147 mm | 5.12 | 0 | 0 | 0 | 0 | 4 | 14 / 20 MT ✗ | 4 / 8 MT ✗ | in band | DEFER — family short of min campaign | ok |  | South has slit this 7 of 7 times
Next cycle |  | SOUTH | — | SHS | 40x40 | 4 | 10 | 4 × 155 mm | 0 | 0 | 0 | 0 | 0 | 10 | 10 / 20 MT ✗ | 10 / 8 MT ✓ | in band | DEFER — family short of min campaign | ok |  | South width from its own 3mm run (4mm never run here)
Next cycle |  | SOUTH | — | SHS | 60x60 | 2 | 6 | 2 × 235 mm | 12.33 | 0.21 | 0 | 0 | 0 | 6 | 6 / 20 MT ✗ | 6 / 12 MT ✗ | BAND EDGE | DEFER — family short of min campaign | ok |  | South has slit this 5 of 12 times
Next cycle |  | SOUTH | — | SHS | 72x72 | 4 | 5 | 4 × 276 mm | 50.43 | 0 | 0 | 0 | 0 | 5 | 39 / 20 MT ✓ | 5 / 8 MT ✗ | in band | DEFER — under gauge floor | ok |  | South has slit this 7 of 7 times
Next cycle |  | SOUTH | — | SHS | 80x80 | 4 | 3 | 4 × 316 mm | 0 | 0 | 0 | 0 | 0 | 3 | 21 / 20 MT ✓ | 3 / 8 MT ✗ | in band | DEFER — under gauge floor | ok |  | company-wide width — South has never run this size
Next cycle |  | SOUTH | — | SHS | 80x80 | 5 | 6 | 5 × 314 mm | 0 | 83.06 | 0 | 0 | 0 | 6 | 21 / 20 MT ✓ | 6 / 8 MT ✗ | in band | DEFER — under gauge floor | ok |  | company-wide width — South has never run this size
Next cycle |  | SOUTH | — | SHS | 100x100 | 2 | 55 | 2 × 398 mm | 0 | 0.21 | 0 | 0 | 0 | 55 | 150 / 20 MT ✓ | 55 / 12 MT ✓ | BAND EDGE | DEFER — only 0.2 MT of coil, under the 12 MT gauge floor | ok | 07 Nov 2026 | South has slit this 6 of 6 times
Next cycle |  | SOUTH | — | SHS | 132x132 | 4 | 2 | 4 × 520 mm | 0 | 0 | 0 | 0 | 0 | 2 | 7 / 20 MT ✗ | 2 / 12 MT ✗ | BAND EDGE | DEFER — family short of min campaign | ok |  | company-wide width — South has never run this size
Next cycle |  | SOUTH | — | SHS | 132x132 | 5 | 5 | 5 × 520 mm | 0 | 83.06 | 0 | 0 | 0 | 5 | 7 / 20 MT ✗ | 5 / 12 MT ✗ | BAND EDGE | DEFER — family short of min campaign | ok |  | company-wide width from 4mm — South has never run this size
Next cycle |  | SOUTH | — | SHS | 150x150 | 2 | 10 | 2 × 597 mm | 0 | 0.21 | 0 | 0 | 0 | 10 | 26 / 20 MT ✓ | 10 / 12 MT ✗ | BAND EDGE | DEFER — under gauge floor | ok |  | South width from its own 3mm run (2mm never run here)
Next cycle |  | SOUTH | — | SHS | 150x150 | 2.5 | 10 | 2.5 × 597 mm | 0 | 71.91 | 0 | 0 | 0 | 10 | 26 / 20 MT ✓ | 10 / 12 MT ✗ | BAND EDGE | DEFER — under gauge floor | ok |  | South width from its own 3mm run (2.5mm never run here)
Next cycle |  | SOUTH | — | SHS | 150x150 | 6 | 6 | 6 × 583 mm | 0 | 0 | 0 | 0 | 0 | 6 | 26 / 20 MT ✓ | 6 / 8 MT ✗ | in band | DEFER — under gauge floor | ok |  | South width from its own 5mm run (6mm never run here)
Next cycle |  | SOUTH | — | RHS | 40x20 | 1.2 | 10 | 1.2 × 117 mm | 0 | 0 | 0 | 0 | 0 | 10 | 46 / 20 MT ✓ | 10 / 12 MT ✗ | BAND EDGE | DEFER — under gauge floor | ok |  | South has slit this 18 of 18 times
Next cycle |  | SOUTH | — | RHS | 40x20 | 1.6 | 30 | 1.6 × 116 mm | 4.22 | 0 | 0 | 0 | 0 | 30 | 46 / 20 MT ✓ | 30 / 8 MT ✓ | in band | DEFER — only 4.1 MT of coil, under the 8 MT gauge floor | ok | 07 Nov 2026 | South has slit this 12 of 27 times
Next cycle |  | SOUTH | — | RHS | 40x20 | 2.5 | 6 | 2.5 × 114 mm | 0 | 71.91 | 0 | 0 | 0 | 6 | 46 / 20 MT ✓ | 6 / 8 MT ✗ | in band | DEFER — under gauge floor | ok |  | South has slit this 9 of 12 times
Next cycle |  | SOUTH | — | RHS | 60x40 | 3 | 6 | 3 × 196 mm | 4.83 | 125.61 | 0 | 0 | 0 | 6 | 68 / 20 MT ✓ | 6 / 8 MT ✗ | in band | DEFER — under gauge floor | ok |  | South width from its own 2.8mm run (3mm never run here)
Next cycle |  | SOUTH | — | RHS | 60x40 | 4 | 2 | 4 × 196 mm | 0 | 0 | 0 | 0 | 0 | 2 | 68 / 20 MT ✓ | 2 / 8 MT ✗ | in band | DEFER — under gauge floor | ok |  | South width from its own 2.8mm run (4mm never run here)
Next cycle |  | SOUTH | — | RHS | 80x40 | 1.6 | 70 | 1.6 × 237 mm | 7.66 | 0 | 0 | 0 | 0 | 70 | 97 / 20 MT ✓ | 70 / 12 MT ✓ | BAND EDGE | DEFER — only 7.4 MT of coil, under the 12 MT gauge floor | ok | 07 Nov 2026 | South has slit this 20 of 32 times
Next cycle |  | SOUTH | — | RHS | 96x48 | 2.8 | 6 | 2.8 × 280 mm | 0 | 154.44 | 0 | 0 | 0 | 6 | 43 / 20 MT ✓ | 6 / 12 MT ✗ | BAND EDGE | DEFER — under gauge floor | ok |  | South width from its own 3mm run (2.8mm never run here)
Next cycle |  | SOUTH | — | RHS | 100x50 | 2.9 | 5 | 2.9 × 295 mm | 0 | 121.4 | 0 | 0 | 0 | 5 | 51 / 20 MT ✓ | 5 / 12 MT ✗ | BAND EDGE | DEFER — under gauge floor | ok |  | South width from its own 2.8mm run (2.9mm never run here)
Next cycle |  | SOUTH | — | RHS | 145x82 | 3 | 3 | 3 × 448 mm | 0 | 121.4 | 0 | 0 | 0 | 3 | 11 / 20 MT ✗ | 3 / 12 MT ✗ | BAND EDGE | DEFER — family short of min campaign | ok |  | company-wide width — South has never run this size
Next cycle |  | SOUTH | — | RHS | 145x82 | 4 | 2 | 4 × 448 mm | 0 | 0 | 0 | 0 | 0 | 2 | 11 / 20 MT ✗ | 2 / 12 MT ✗ | BAND EDGE | DEFER — family short of min campaign | ok |  | company-wide width — South has never run this size
Next cycle |  | SOUTH | — | RHS | 145x82 | 5 | 6 | 5 × 448 mm | 0 | 83.06 | 0 | 0 | 0 | 6 | 11 / 20 MT ✗ | 6 / 8 MT ✗ | in band | DEFER — family short of min campaign | ok |  | company-wide width from 4mm — South has never run this size
Next cycle |  | SOUTH | — | RHS | 200x100 | 6 | 5 | 6 × 596 mm | 0 | 0 | 0 | 0 | 0 | 5 | 5 / 20 MT ✗ | 5 / 8 MT ✗ | in band | DEFER — family short of min campaign | ok |  | company-wide width from 5mm — South has never run this size
Next cycle |  | WEST | — | CHS | 15 NB | 2 | 2 | 2 × 64 mm | 0 | 0 | 0 | 0 | 0 | 2 | 2 / 20 MT ✗ | 2 / 12 MT ✗ | BAND EDGE | DEFER — family short of min campaign | ok |  | company-wide width — West has never run this size
Next cycle |  | WEST | — | CHS | 20 NB | 2 | 7 | 2 × 76 mm | 0 | 0 | 0 | 0 | 0 | 7 | 12 / 20 MT ✗ | 7 / 8 MT ✗ | in band | DEFER — family short of min campaign | ok |  | company-wide width — West has never run this size
Next cycle |  | WEST | — | CHS | 25 NB | 2 | 5 | 2 × 96 mm | 0 | 0 | 0 | 0 | 0 | 5 | 7 / 20 MT ✗ | 5 / 8 MT ✗ | in band | DEFER — family short of min campaign | ok |  | company-wide width — West has never run this size
Next cycle |  | WEST | — | CHS | 25 NB | 2.5 | 2 | 2.3 × 97 mm | 0 | 49 | 0 | 0 | 0 | 2 | 7 / 20 MT ✗ | 2 / 8 MT ✗ | in band | DEFER — family short of min campaign | ok |  | company-wide width — West has never run this size
Next cycle |  | WEST | — | CHS | 32 NB | 2 | 3 | 2 × 130 mm | 0 | 0 | 0 | 0 | 0 | 3 | 11 / 20 MT ✗ | 3 / 8 MT ✗ | in band | DEFER — family short of min campaign | ok |  | company-wide width — West has never run this size
Next cycle |  | WEST | — | CHS | 32 NB | 2.5 | 4 | 2.5 × 128 mm | 0 | 49 | 0 | 0 | 0 | 4 | 11 / 20 MT ✗ | 4 / 8 MT ✗ | in band | DEFER — family short of min campaign | ok |  | company-wide width — West has never run this size
Next cycle |  | WEST | — | CHS | 40 NB | 2.5 | 5 | 2.3 × 150 mm | 4.74 | 49 | 0 | 0 | 0 | 5 | 14 / 20 MT ✗ | 5 / 8 MT ✗ | in band | DEFER — family short of min campaign | ok |  | company-wide width — West has never run this size
Next cycle |  | WEST | — | CHS | 50 NB | 2 | 2 | 2 × 186 mm | 0 | 0 | 0 | 0 | 0 | 2 | 9 / 20 MT ✗ | 2 / 8 MT ✗ | in band | DEFER — family short of min campaign | ok |  | company-wide width — West has never run this size
Next cycle |  | WEST | — | CHS | 50 NB | 4 | 2 | 4 × 182 mm | 0 | 0 | 0 | 0 | 0 | 2 | 9 / 20 MT ✗ | 2 / 8 MT ✗ | in band | DEFER — family short of min campaign | ok |  | company-wide width — West has never run this size
Next cycle |  | WEST | — | CHS | 65 NB | 2.5 | 2 | 2.5 × 235 mm | 9.33 | 49 | 0 | 0 | 0 | 2 | 2 / 20 MT ✗ | 2 / 8 MT ✗ | in band | DEFER — family short of min campaign | ok |  | company-wide width — West has never run this size
Next cycle |  | WEST | — | CHS | 80 NB | 4 | 7 | 4 × 270 mm | 0 | 0 | 0 | 0 | 0 | 7 | 7 / 20 MT ✗ | 7 / 8 MT ✗ | in band | DEFER — family short of min campaign | ok |  | company-wide width — West has never run this size
Next cycle |  | WEST | — | SHS | 25x25 | 1.2 | 20 | 1.2 × 97 mm | 0.97 | 0 | 0 | 0 | 0 | 20 | 71 / 20 MT ✓ | 20 / 8 MT ✓ | in band | DEFER — only 0.9 MT of coil, under the 8 MT gauge floor | ok | 07 Nov 2026 | company-wide width — West has never run this size
Next cycle |  | WEST | — | SHS | 30x30 | 2 | 5 | 2 × 116 mm | 0 | 0 | 0 | 0 | 0 | 5 | 5 / 20 MT ✗ | 5 / 8 MT ✗ | in band | DEFER — family short of min campaign | ok |  | company-wide width — West has never run this size
Next cycle |  | WEST | — | SHS | 60x60 | 2 | 7 | 2 × 235 mm | 0 | 0 | 0 | 0 | 0 | 7 | 56 / 20 MT ✓ | 7 / 12 MT ✗ | BAND EDGE | DEFER — under gauge floor | ok |  | company-wide width — West has never run this size
Next cycle |  | WEST | — | SHS | 60x60 | 2.5 | 4 | 2.5 × 235 mm | 9.33 | 11.5 | 0 | 0 | 0 | 4 | 56 / 20 MT ✓ | 4 / 8 MT ✗ | in band | DEFER — under gauge floor | ok |  | company-wide width — West has never run this size
Next cycle |  | WEST | — | SHS | 80x80 | 6 | 10 | 6 × 314 mm | 5.98 | 0 | 0 | 0 | 0 | 10 | 49 / 20 MT ✓ | 10 / 8 MT ✓ | in band | DEFER — only 5.7 MT of coil, under the 8 MT gauge floor | ok | 07 Nov 2026 | West width from its own 5mm run (6mm never run here)
Next cycle |  | WEST | — | SHS | 132x132 | 5 | 15 | 5 × 520 mm | 0 | 0 | 0 | 0 | 0 | 15 | 18 / 20 MT ✗ | 15 / 12 MT ✓ | BAND EDGE | DEFER — family short of min campaign | ok |  | West width from its own 4mm run (5mm never run here)
Next cycle |  | WEST | — | SHS | 132x132 | 6 | 3 | 6 × 520 mm | 0 | 0 | 0 | 0 | 0 | 3 | 18 / 20 MT ✗ | 3 / 8 MT ✗ | in band | DEFER — family short of min campaign | ok |  | West width from its own 4mm run (6mm never run here)
Next cycle |  | WEST | — | RHS | 40x20 | 1.2 | 5 | 1.2 × 117 mm | 0 | 0 | 0 | 0 | 0 | 5 | 37 / 20 MT ✓ | 5 / 12 MT ✗ | BAND EDGE | DEFER — under gauge floor | ok |  | company-wide width — West has never run this size
Next cycle |  | WEST | — | RHS | 40x20 | 2.5 | 3 | 2.5 × 114 mm | 0 | 11.5 | 0 | 0 | 0 | 3 | 37 / 20 MT ✓ | 3 / 8 MT ✗ | in band | DEFER — under gauge floor | ok |  | company-wide width — West has never run this size
Next cycle |  | WEST | — | RHS | 40x20 | 3 | 3 | 3 × 116 mm | 0 | 18.23 | 0 | 0 | 0 | 3 | 37 / 20 MT ✓ | 3 / 8 MT ✗ | in band | DEFER — under gauge floor | ok |  | company-wide width — West has never run this size
Next cycle |  | WEST | — | RHS | 50x25 | 2 | 31 | 2 × 149 mm | 4.74 | 0 | 0 | 0 | 0 | 31 | 67 / 20 MT ✓ | 31 / 8 MT ✓ | in band | DEFER — only 4.6 MT of coil, under the 8 MT gauge floor | ok | 07 Nov 2026 | West width from its own 1.6mm run (2mm never run here)
Next cycle |  | WEST | — | RHS | 75x25 | 2 | 5 | 2 × 197 mm | 15.88 | 0 | 0 | 0 | 0 | 5 | 8 / 20 MT ✗ | 5 / 8 MT ✗ | in band | DEFER — family short of min campaign | ok |  | company-wide width — West has never run this size
Next cycle |  | WEST | — | RHS | 75x25 | 2.5 | 3 | 2.3 × 196 mm | 31.34 | 0.04 | 0 | 0 | 0 | 3 | 8 / 20 MT ✗ | 3 / 8 MT ✗ | in band | DEFER — family short of min campaign | ok |  | company-wide width — West has never run this size
Next cycle |  | WEST | — | RHS | 96x48 | 5 | 19 | 5 × 282 mm | 0 | 0 | 0 | 0 | 0 | 19 | 19 / 20 MT ✗ | 19 / 8 MT ✓ | in band | DEFER — family short of min campaign | ok |  | West has slit this 4 of 4 times
Next cycle |  | WEST | — | RHS | 100x50 | 2 | 2 | 2 × 296 mm | 0 | 0 | 0 | 0 | 0 | 2 | 11 / 20 MT ✗ | 2 / 12 MT ✗ | BAND EDGE | DEFER — family short of min campaign | ok |  | company-wide width — West has never run this size
Next cycle |  | WEST | — | RHS | 100x50 | 2.5 | 2 | 2.5 × 293 mm | 0 | 0.04 | 0 | 0 | 0 | 2 | 11 / 20 MT ✗ | 2 / 12 MT ✗ | BAND EDGE | DEFER — family short of min campaign | ok |  | company-wide width — West has never run this size
Next cycle |  | WEST | — | RHS | 100x50 | 3 | 2 | 3 × 293 mm | 0 | 18.23 | 0 | 0 | 0 | 2 | 11 / 20 MT ✗ | 2 / 8 MT ✗ | in band | DEFER — family short of min campaign | ok |  | company-wide width — West has never run this size
Next cycle |  | WEST | — | RHS | 100x50 | 4 | 5 | 4 × 292 mm | 0 | 0 | 0 | 0 | 0 | 5 | 11 / 20 MT ✗ | 5 / 8 MT ✗ | in band | DEFER — family short of min campaign | ok |  | company-wide width — West has never run this size
[6 empty] | TOTAL | 2138 |  |  |  | 204.4 | 326 | 509.2 | 1628.8
Reconciliation (ADR-0001 identity, nothing netted):
Qty left with no stock, both regions | [6 empty] | 2138
Planned this cycle (W1–W4) | [6 empty] | 509.21
Deferred — family under min campaign | [6 empty] | 184
Deferred — cell under gauge floor | [6 empty] | 426
Blocked — no coil of that spec | [6 empty] | 713
Run short — coil ran out mid-cell | [6 empty] | 42.79
Blocked — no SKU master row | [6 empty] | 191
Blocked — no slitting spec (width) | [6 empty] | 72
— coil on hand at the start (MT) | [6 empty] | 1805.21
— coil consumed by this plan (MT) | [6 empty] | 530.43
— coil left unused (wrong spec for what is owed) | [6 empty] | 1274.78
Flags: 39 of 171 demand cells have NO SKU master row (column "SKU master") — the size/gauge is not in the catalog, so there is no weightPerTube to produce against. None is planned — each is blocked and its coil released to a family that can run.
12 cells have no slitting spec at all (no width ever established for that size, anywhere): SOUTH CHS 100 NB; SOUTH RHS 95x25; WEST RHS 172x92; WEST RHS 240x120; WEST SHS 180x180; WEST SHS 32x32. Establish the slit width and these become plannable.
Also: the plants master table is EMPTY, so the service area (Hyderabad+Lepakshi = South, NPMD+Tapi = West) is taken from CLAUDE.md, not from plants.serves. And WEST "RHS 18x180" in the source sheet is almost certainly a transposed 180x18.
What this plan does NOT cover: demand is the no-stock back order only — not the rest of the order book, not the best estimate, not stock cover. A family that defers on the min-campaign test may well clear it once the full order book is added. Mill-level sequencing, changeover hours and roll-set capability are not modelled (the plant/mill capability matrix does not exist — design ticket 04). Coil is matched on thickness ±0.35 mm and width ±3 mm, against widths the REGION has actually slit; where the region has never run a size, a company-wide width is used and the "Width basis" column says so.